**Production Schedule [Sample]**

**[Pre-production Stage]** March 2022 - January 2023

Script development and funding March 2022 - May 2022

Script revision and script lock May 2022 - October 2022

Casting and location hunting October 2022 - December 2022

Equipment and staff hiring December 2022 - January 2023

**[Production Stage]** February 2023 - May 2023

Shooting February 2023 - May 2023

**[Post Production Stage]** June 2023 - October 2023

Editing and final cut June 2023 - August 2023

Color correction and telecine August 2023 - September 2023

Sound design and final mixing August 2023 - October 2023

Final version in screening format October 2023

Theatrical Release Date: December 2023

**※** *This schedule is provided just as a sample. Please modify in detail according to your own project situation.*