**Production Schedule [Sample]**

**[Pre-production Stage]** March 2023 - January 2024

Script development and funding March 2023 - May 2023

Script revision and script lock May 2023 - October 2023

Casting and location hunting October 2023 - December 2023

Equipment and staff hiring December 2023 - January 2024

**[Production Stage]** February 2024 - May 2024

Shooting February 2024 - May 2024

**[Post Production Stage]** June 2024 - October 2024

Editing and final cut June 2024 - August 2024

Color correction and telecine August 2024 - September 2024

Sound design and final mixing August 2024 - October 2024

Final version in screening format October 2024

Theatrical Release Date: December 2024

**※** *This schedule is provided just as a sample. Please modify in detail according to your own project situation.*