**Production Schedule [Sample]**

**[Pre-production Stage]** March 2024 - January 2025

Script development and funding March 2024 - May 2024

Script revision and script lock May 2024 - October 2024

Casting and location hunting October 2024 - December 2024

Equipment and staff hiring December 2024 - January 2025

**[Production Stage]** February 2025 - May 2025

Shooting February 2025 - May 2025

**[Post Production Stage]** June 2025 - October 2025

Editing and final cut June 2025 - August 2025

Color correction and telecine August 2025 - September 2025

Sound design and final mixing August 2025 - October 2025

Final version in screening format October 2025

Theatrical Release Date: December 2025

**※** *This schedule is provided just as a sample. Please modify in detail according to your own project situation.*