**Production Schedule [Sample]**

**[Pre-production Stage]** March 2025 - January 2026

Script development and funding March 2025 - May 2025

Script revision and script lock May 2025 - October 2025

Casting and location hunting October 2025 - December 2025

Equipment and staff hiring December 2025 - January 2026

**[Production Stage]** February 2026 - May 2026

Shooting February 2026 - May 2026

**[Post Production Stage]** June 2026 - October 2026

Editing and final cut June 2026 - August 2026

Color correction and telecine August 2026 - September 2026

Sound design and final mixing August 2026 - October 2026

Final version in screening format October 2026

Theatrical Release Date: January 2026

**※** *This schedule is provided just as a sample. Please modify in detail according to your own project situation.*